## Instructions
Instructions
To Refresh the data (i.e. pull the latest Synergy):
Filters - Uncheck projects with £0 residual fee. This hides projects with nothing to forecast.
Filter by Discupline and PM to get to your projects.
Forecast - Based on your knowledge of the project programme, manually enter your best guess of the invoicing value for the next 6 months.
Update Forecast - On the forecast tab, refresh the data.

## SynergyModel 1
Data returned for SynergyModel 1.
Projects[Project Number] | Projects[name] | Stages[name] | Stages[manager] | Stages[discipline] | Stages[status] | [Agreed_Fee_and_Cap] | [Invoiced_Ex_Tax] | [Residual] | [WIP] | Forecast This Month | Forecast Next Month | Forecast Month +2 | Forecast Month +3 | Forecast Month +4 | Forecast Month +5 | Forecast Beyond
P1361 | Riverbank School, Aberdeen | Noise Impact Assessment revision | Nick Swainston | Acoustics | Active | 1500 | 1500 | 0 | 0 | [6 empty] | 0
P1361 | Riverbank School, Aberdeen | Stage 4 update | Nick Swainston | Acoustics | Active | 2350 | 2350 | 0 | 0 | [6 empty] | 0
P1361 | Riverbank School, Aberdeen | Stage 5 | Nick Swainston | Acoustics | Active | 5985 | 2992 | 2992 | 230 | 2992 | [5 empty] | 0
P1517 | Newcourt Street, London | Acosutic Testing | Mark Scaife | Acoustics | Active | 950 | 0 | 950 | 0 |  | 950 |  |  |  |  | 0
P1517 | Newcourt Street, London | Acoustic - Planning Condition Report | Mark Scaife | Acoustics | Active | 2500 | 550 | 1950 | 0 | 1000 | 950 |  |  |  |  | 0
P1517 | Newcourt Street, London | Acoustic Site Inspection | Mark Scaife | Acoustics | Active | 995 | 995 | 0 | 1225.17 | [6 empty] | 0
P1517 | Newcourt Street, London | Construction Stage - Acoustics | Mark Scaife | Acoustics | Active | 3750 | 1000 | 2750 | 0 | 1500 | 1250 |  |  |  |  | 0
P1517 | Newcourt Street, London | Construction Stage- Fire | Ben Cahill | Fire | Active | 7900 | 6320 | 1580 | 0 | [6 empty] | 1580
P1517 | Newcourt Street, London | RIBA Stage 3: Schematic Design - Fire | Ben Cahill | Fire | Active | 2500 | 2500 | 0 | 0 | [6 empty] | 0
P1517 | Newcourt Street, London | RIBA Stage 4 : Detailed Design - Fire | Ben Cahill | Fire | Active | 2500 | 2500 | 0 | 1175 | [6 empty] | 0
P1517 | Newcourt Street, London | RIBA Stage2 : Concept Design - Fire | Ben Cahill | Fire | Active | 1500 | 0 | 1500 | 0 | [6 empty] | 1500
P1548 | London Bridge Station | Grip 5 | Ben Cahill | Fire | Construction | 3100 | 3100 | 0 | 500 | [6 empty] | 0
P1548 | London Bridge Station | Grip 6 | Ben Cahill | Fire | Construction | 13800 | 8280 | 5520 | 330 | 5520 | [5 empty] | 0
P1580 | Eastern Base | RIBA Stage 4 Fire PO: 985301 | Ben Cahill | Fire | Active | 9800 | 9800 | 0 | 70 | [6 empty] | 0
P1580 | Eastern Base | RIBA Stage 5 Fire PO: 1077320 | Ben Cahill | Fire | Active | 14600 | 730 | 13870 | 0 | [6 empty] | 13870
P1580 | Eastern Base | RIBA Stage 5, 6 & 7 PO: 985301 | Ben Cahill | Fire | Active | 14000 | 0 | 14000 | 0 | [6 empty] | 14000
P1580 | Eastern Base | Stage 5 Acoustics - PO:1026106 | Nick Swainston | Acoustics | Active | 2940 | 1323 | 1617 | 0 | 1000 | 617 |  |  |  |  | 0
P1580 | Eastern Base | Stage 6 Acoustics PO: 1026106 | Nick Swainston | Acoustics | Active | 2680 | 0 | 2680 | 0 |  |  | 1000 | 1000 | 680 |  | 0
P1580 | Eastern Base | Stage 7 Acoustics PO : 1026106 | Nick Swainston | Acoustics | Active | 1320 | 0 | 1320 | 0 | [5 empty] | 1320 | 0
P1584 | The Savoy Guest Room | 2 * Site Visits & Reporting - Fire - Work Package B | Terry Marsh | Fire | Active | 2400 | 0 | 2400 | 0 |  |  | 2400 |  |  |  | 0
P1584 | The Savoy Guest Room | 3 * Site Visits & Reporting - Fire - Work Package A | Ben Cahill | Fire | Active | 3600 | 3600 | 0 | 490 | [6 empty] | 0
P1584 | The Savoy Guest Room | Compliance statement - work Package A | Mark Scaife | Fire | Active | 4000 | 4000 | 0 | 0 | [6 empty] | 0
P1584 | The Savoy Guest Room | Construction Stage support - Acoustics - Work Package A | Mark Scaife | Acoustics | Active | 1350 | 1012 | 338 | 1260 |  | 338 |  |  |  |  | 0
P1584 | The Savoy Guest Room | Construction Stage support - Acoustics - Work Package B | Mark Scaife | Acoustics | Active | 900 | 0 | 900 | 0 |  |  | 0 |  | 900 |  | 0
P1584 | The Savoy Guest Room | RIBA Stage 5 Support - FIRE - Work Package A | Ben Cahill | Fire | Active | 6000 | 6000 | 0 | 2100 | [6 empty] | 0
P1584 | The Savoy Guest Room | RIBA Stage 5 Support - FIRE - Work Package B | Terry Marsh | Fire | Active | 4000 | 0 | 4000 | 165 |  |  | 4000 |  |  |  | 0
P1584 | The Savoy Guest Room | Sectional Completion Specific Fire Strategy Report - Work Package A | Mark Scaife | Fire | Active | 1750 | 1750 | 0 | 0 | [6 empty] | 0
P1584 | The Savoy Guest Room | Site inspections (up to 4 visits, meetings) - Acoustics - Work Package B | Mark Scaife | Acoustics | Active | 3200 | 0 | 3200 | 0 | [5 empty] | 1600 | 1600
P1584 | The Savoy Guest Room | Site inspections (up to 6 visits, meetings) - Acoustics - Work Package A | Mark Scaife | Acoustics | Active | 4800 | 3200 | 1600 | 712.66 |  |  | 800 |  | 800 |  | 0
P1600 | Leinster House | Additional Noise Survey | Mark Scaife | Acoustics | Active | 1540 | 1540 | 0 | 0 | [6 empty] | 0
P1600 | Leinster House | FCU Mock Up Testing | Mark Scaife | Acoustics | Active | 950 | 950 | 0 | 0 | [6 empty] | 0
P1600 | Leinster House | Site Inspection | Mark Scaife | Acoustics | Active | 1500 | 0 | 1500 | 0 |  | 1500 |  |  |  |  | 0
P1600 | Leinster House | Stage 5 Design Suport | Mark Scaife | Acoustics | Active | 2400 | 2280 | 120 | 393.75 | 120 | [5 empty] | 0
P1617 | Brooklands College Education Buildings | Additional site visit (P100008086) | Ben Cahill | Fire | Active | 950 | 950 | 0 | 0 | [6 empty] | 0
P1617 | Brooklands College Education Buildings | Additional works | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P1618 | Haverstock Hill | Response to LFB Comments | Terry Marsh | Fire | Active | 3000 | 3000 | 0 | 0 | [6 empty] | 0
P1629 | Heath Road East Bergholt | BREEAM/PCT Testing | Joe Conaghan | Acoustics | Active | 1150 | 0 | 1150 | 0 |  | 1150 |  |  |  |  | 0
P1629 | Heath Road East Bergholt | Report Review | Joe Conaghan | Acoustics | Active | 950 | 950 | 0 | 0 | [6 empty] | 0
P1635 | Lowestoft Town Hall | RIBA Stage 2 | Ben Cahill | Fire | Active | 1400 | 1400 | 0 | 0 | [6 empty] | 0
P1635 | Lowestoft Town Hall | RIBA Stage 3 | Ben Cahill | Fire | Active | 2800 | 2800 | 0 | 0 | [6 empty] | 0
P1635 | Lowestoft Town Hall | RIBA Stage 4 | Ben Cahill | Fire | Active | 2800 | 2800 | 0 | 0 | [6 empty] | 0
P1635 | Lowestoft Town Hall | RIBA Stage 5 | Rob Holland | Fire | Construction | 8000 | 0 | 8000 | 62.5 | [6 empty] | 8000
P1638 | Northern Arc | RIBA Stage 3 | Rob Holland | Fire | Active | 56500 | 56500 | 0 | 0 | [6 empty] | 0
P1638 | Northern Arc | RIBA Stage 4 | Rob Holland | Fire | Active | 8500 | 0 | 8500 | 71.25 | [6 empty] | 8500
P1638 | Northern Arc | RIBA Stage 5 | Rob Holland | Fire | Active | 10000 | 0 | 10000 | 0 | [6 empty] | 10000
P1638 | Northern Arc | Stage 6 Fire Risk Assessments | Ben Cahill | Fire | Active | 17000 | 0 | 17000 | 0 | [6 empty] | 17000
P1671 | Deben Fields, Felixstowe | RIBA Stage 4 Fire | Rob Holland | Fire | Construction | 17280 | 17280 | 0 | 397.15 | [6 empty] | 0
P1671 | Deben Fields, Felixstowe | RIBA Stage 5 FIRE | Rob Holland | Fire | Construction | 8900 | 5785 | 4450 | 4173.73 |  |  | 2225 |  |  | 2225 | 0
P1671 | Deben Fields, Felixstowe | Stage 5 - Construction Phase Acoustics | Joe Conaghan | Acoustics | Active | 769.5 | 770 | 0 | 1845.48 | [6 empty] | 0
P1671 | Deben Fields, Felixstowe | Stage 6 - Handover and Pre-completion Testing Acoustics | Joe Conaghan | Acoustics | Active | 2300 | 1725 | 1725 | 0 | [6 empty] | 1725
P1675 | Brooklands Ashford T-level | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P1675 | Brooklands Ashford T-level | RIBA Stage 3 - Spatial Coordination - Fire | Ben Cahill | Fire | Active | 4500 | 4500 | 0 | 235 | [6 empty] | 0
P1675 | Brooklands Ashford T-level | RIBA Stage 4 - Technical Design - Fire | Ben Cahill | Fire | Active | 4500 | 0 | 4500 | 55 | [6 empty] | 4500
P1681 | Great Sutton Medical Centre | Acoustic Commissioning (HEA05) @ Site Near Elsmere Port | Nick Swainston | Acoustics | Active | 1975 | 0 | 1975 | 0 |  | 1975 |  |  |  |  | 0
P1683 | Brooklands College Apartments & Houses | Stage 2 Fire | Rob Holland | Fire | Active | 10800 | 10800 | 0 | 0 | [6 empty] | 0
P1683 | Brooklands College Apartments & Houses | Stage 4 Fire | Rob Holland | Fire | Active | 37500 | 28125 | 9375 | 1170 |  | 3125 |  | 3125 |  | 3125 | 0
P1702 | Teaching Building- UOW- Acoustics | Contingency - Uplift for PO to Complete the project | Nick Swainston | Acoustics | Active | 9000 | 4870 | 4130 | 110 | [6 empty] | 4130
P1702 | Teaching Building- UOW- Acoustics | Professional services | Nick Swainston | Acoustics | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P1702 | Teaching Building- UOW- Acoustics | Stage 3 -Schematic Design | Nick Swainston | Acoustics | Active | 2750 | 2750 | 0 | 0 | [6 empty] | 0
P1702 | Teaching Building- UOW- Acoustics | Stage 4 -Detailed Design | Nick Swainston | Acoustics | Active | 4985 | 4985 | 0 | 0 | [6 empty] | 0
P1702 | Teaching Building- UOW- Acoustics | Stage 5 & 6 - Construction & Commissioning | Nick Swainston | Acoustics | Active | 7495 | 7495 | 0 | 0 | [6 empty] | 0
P1703 | 9-12 Bow Street | Construction Stage - Design Reviews Acoustic | Joe Conaghan | Acoustics | Active | 1000 | 0 | 1000 | 0 | 250 | 250 | 250 | 250 |  |  | 0
P1703 | 9-12 Bow Street | Construction Stage - Site Inspection Acoustic | Joe Conaghan | Acoustics | Active | 700 | 0 | 700 | 0 | [6 empty] | 700
P1703 | 9-12 Bow Street | Construction Stage - Testing Acoustic | Joe Conaghan | Acoustics | Active | 1100 | 0 | 1100 | 0 | [6 empty] | 1100
P1703 | 9-12 Bow Street | RIBA Stage 4 Fire | Ben Cahill | Fire | Active | 6900 | 6900 | 0 | 845 | [6 empty] | 0
P1703 | 9-12 Bow Street | RIBA Stage 5 - Contract Documentation Acoustic | Joe Conaghan | Acoustics | Active | 1500 | 0 | 1500 | 120 | [6 empty] | 1500
P1703 | 9-12 Bow Street | RIBA Stage 5 FIRE | Ben Cahill | Fire | Active | 4400 | 0 | 4400 | 0 | [6 empty] | 4400
P1704 | 50 Floral Street | Construction Stage - Design Reviews Acoustic | Joe Conaghan | Acoustics | Active | 1000 | 0 | 1000 | 0 | 250 | 250 | 250 | 250 |  |  | 0
P1704 | 50 Floral Street | Construction Stage - Site Inspection Acoustic | Joe Conaghan | Acoustics | Active | 700 | 0 | 700 | 0 | [6 empty] | 700
P1704 | 50 Floral Street | Construction Stage - Testing Acoustic | Joe Conaghan | Acoustics | Active | 1100 | 0 | 1100 | 0 | [6 empty] | 1100
P1704 | 50 Floral Street | Design Verification Fire | Ben Cahill | Fire | Active | 1500 | 1500 | 0 | 750 | [6 empty] | 0
P1704 | 50 Floral Street | RIBA Stage 5 - Contract Documentation Acoustic | Joe Conaghan | Acoustics | Active | 1500 | 0 | 1500 | 0 | [6 empty] | 1500
P1704 | 50 Floral Street | RIBA Stage 5 FIRE | Ben Cahill | Fire | Active | 4400 | 0 | 4400 | 0 | [6 empty] | 4400
P1707 | East Coast College, Great Yarmouth | Additional Acoustic Items | Joe Conaghan | Acoustics | Active | 1970 | 1970 | 0 | 0 | [6 empty] | 0
P1707 | East Coast College, Great Yarmouth | Additional RIBA Stage 2 / 3 Support Fire | Ben Cahill | Fire | Active | 7500 | 7500 | 0 | 25 | [6 empty] | 0
P1707 | East Coast College, Great Yarmouth | Architectural Acoustics | Joe Conaghan | Acoustics | Active | 4950 | 4950 | 0 | 0 | [6 empty] | 0
P1707 | East Coast College, Great Yarmouth | Building Services Acoustics | Joe Conaghan | Acoustics | Active | 4500 | 4500 | 0 | 0 | [6 empty] | 0
P1707 | East Coast College, Great Yarmouth | Construction Noise Assessment | Joe Conaghan | Acoustics | Active | 3250 | 3250 | 0 | 0 | [6 empty] | 0
P1707 | East Coast College, Great Yarmouth | Initial Services Acoustics | Joe Conaghan | Acoustics | Active | 2750 | 2750 | 0 | 0 | [6 empty] | 0
P1707 | East Coast College, Great Yarmouth | Pre-completion Testing (2 visits) | Joe Conaghan | Acoustics | Active | 3950 | 0 | 3950 | 0 | [6 empty] | 3950
P1707 | East Coast College, Great Yarmouth | RIBA Stage 2 Fire | Ben Cahill | Fire | Active | 5900 | 5900 | 0 | 0 | [6 empty] | 0
P1707 | East Coast College, Great Yarmouth | RIBA Stage 3 Fire | Ben Cahill | Fire | Active | 7900 | 7900 | 0 | 0 | [6 empty] | 0
P1707 | East Coast College, Great Yarmouth | RIBA Stage 4 Fire | Ben Cahill | Fire | Active | 7900 | 7900 | 0 | 140 | [6 empty] | 0
P1707 | East Coast College, Great Yarmouth | RIBA Stage 5 FIRE | Ben Cahill | Fire | Active | 8300 | 0 | 8300 | 110 |  |  | 2000 |  |  | 2000 | 4300
P1707 | East Coast College, Great Yarmouth | RIBA Stage 6 Fire | Ben Cahill | Fire | Active | 2900 | 0 | 2900 | 0 | [6 empty] | 2900
P1707 | East Coast College, Great Yarmouth | Site Inspections (3 visitis) | Joe Conaghan | Acoustics | Active | 2250 | 0 | 2250 | 0 |  |  |  | 750 | 750 | 750 | 0
P1710 | DoubleTree Hilton, Victoria | RIBA Stage 4 | Ben Cahill | Fire | Active | 7600 | 7600 | 0 | 110 | [6 empty] | 0
P1710 | DoubleTree Hilton, Victoria | RIBA Stage 5 | Ben Cahill | Fire | Active | 6000 | 4200 | 1800 | 0 | 1800 | [5 empty] | 0
P1714 | The Stage Buildings 2, 3, 4, 6 & 7 | Defect Liability Compliance Statement Building 6 | Rob Holland | Fire | Active | 4500 | 4500 | 0 | 0 | [6 empty] | 0
P1714 | The Stage Buildings 2, 3, 4, 6 & 7 | Defects Liability Compliance Statement Building 1 | Rob Holland | Fire | Active | 4500 | 4500 | 0 | 542.64 | [6 empty] | 0
P1714 | The Stage Buildings 2, 3, 4, 6 & 7 | Defects Liability Compliance Statement Building 5 | Rob Holland | Fire | Active | 4500 | 4500 | 0 | 0 | [6 empty] | 0
P1714 | The Stage Buildings 2, 3, 4, 6 & 7 | Defects Liability Compliance Statement Building 7 | Rob Holland | Fire | Active | 4500 | 4500 | 0 | 0 | [6 empty] | 0
P1714 | The Stage Buildings 2, 3, 4, 6 & 7 | Fire Compliance Statement Building 2 | Rob Holland | Fire | Active | 5500 | 5500 | 0 | 0 | [6 empty] | 0
P1714 | The Stage Buildings 2, 3, 4, 6 & 7 | Fire Compliance Statement Building 3 | Rob Holland | Fire | Active | 5500 | 5500 | 0 | 0 | [6 empty] | 0
P1714 | The Stage Buildings 2, 3, 4, 6 & 7 | Fire Compliance Statement Building 4 | Ben Cahill | Fire | Active | 4200 | 4200 | 0 | 0 | [6 empty] | 0
P1714 | The Stage Buildings 2, 3, 4, 6 & 7 | Fire Compliance Statement Building 6 | Ben Cahill | Fire | Active | 4500 | 4500 | 0 | 70 | [6 empty] | 0
P1714 | The Stage Buildings 2, 3, 4, 6 & 7 | Fire Compliance Statement Building 7 | Ben Cahill | Fire | Active | 5500 | 5500 | 0 | 0 | [6 empty] | 0
P1717 | Old Shire Hall, Bury St Edmunds | Construction Stage Fire | Rob Holland | Fire | Active | 5400 | 0 | 5400 | 0 | [6 empty] | 5400
P1717 | Old Shire Hall, Bury St Edmunds | Design Stage Support - Fire | Rob Holland | Fire | Active | 6300 | 6300 | 0 | 1800 | [6 empty] | 0
P1717 | Old Shire Hall, Bury St Edmunds | Stage 4 - Technical Design Acoustic | Joe Conaghan | Acoustics | Active | 4550 | 4550 | 0 | 0 | [6 empty] | 0
P1717 | Old Shire Hall, Bury St Edmunds | Stage 5 - Construction RFI's Acoustic | Joe Conaghan | Acoustics | Active | 1300 | 0 | 1300 | 0 | [6 empty] | 1300
P1717 | Old Shire Hall, Bury St Edmunds | Stage 5 - Site Inspections Acoustic | Joe Conaghan | Acoustics | Active | 800 | 0 | 800 | 0 | [6 empty] | 800
P1717 | Old Shire Hall, Bury St Edmunds | Stage 5 - Testing Acoustic | Joe Conaghan | Acoustics | Active | 2000 | 0 | 2000 | 0 | [6 empty] | 2000
P1722 | Chiswick High Road | Construction Stage - Design Reviews Acoustics | Joe Conaghan | Acoustics | Active | 1200 | 606 | 594 | 0 | 594 | [5 empty] | 0
P1722 | Chiswick High Road | Construction Stage - Site Inspection Acoustics | Joe Conaghan | Acoustics | Active | 750 | 750 | 0 | 0 | [6 empty] | 0
P1722 | Chiswick High Road | Construction Stage - Testing Acoustics | Joe Conaghan | Acoustics | Active | 2000 | 0 | 2000 | 0 |  |  | 1000 | 1000 |  |  | 0
P1722 | Chiswick High Road | RIBA Stage 4 - Technical Design Acoustic | Joe Conaghan | Acoustics | Active | 3950 | 3950 | 0 | 0 | [6 empty] | 0
P1722 | Chiswick High Road | Stage 4 Fire | Ben Cahill | Fire | Active | 8500 | 8500 | 0 | 330 | [6 empty] | 0
P1722 | Chiswick High Road | Stage 5 Fire | Ben Cahill | Fire | Active | 7000 | 3906 | 3094 | 0 | [6 empty] | 3094
P2034 | Arbury Court Steel Remediation | Additional Cavity Barrier Works C2 | Ben Cahill | Fire | Active | 1400 | 1400 | 0 | 0 | [6 empty] | 0
P2034 | Arbury Court Steel Remediation | Additional Site Visits * 10 | Ben Cahill | Fire | Active | 20000 | 10000 | 10000 | 0 | [6 empty] | 10000
P2034 | Arbury Court Steel Remediation | Beam protection x 2 variations | Ben Cahill | Fire | Active | 2800 | 2800 | 0 | 0 | [6 empty] | 0
P2034 | Arbury Court Steel Remediation | Column protection x 2 variations | Ben Cahill | Fire | Active | 2800 | 2800 | 0 | 0 | [6 empty] | 0
P2034 | Arbury Court Steel Remediation | Construction Phase Fire Straegy Report (3 Scenarios) | Ben Cahill | Fire | Active | 13200 | 13200 | 0 | 0 | [6 empty] | 0
P2034 | Arbury Court Steel Remediation | Corridor Beam protection x 3 variations | Ben Cahill | Fire | Active | 4200 | 4200 | 0 | 0 | [6 empty] | 0
P2034 | Arbury Court Steel Remediation | FRAEW | Ben Cahill | Fire | Active | 7885 | 7885 | 0 | 0 | [6 empty] | 0
P2034 | Arbury Court Steel Remediation | General Advice | Ben Cahill | Fire | Active | 2800 | 2800 | 0 | 0 | [6 empty] | 0
P2034 | Arbury Court Steel Remediation | Site Visits (12) | Ben Cahill | Fire | Active | 24000 | 24000 | 0 | 0 | [6 empty] | 0
P2034 | Arbury Court Steel Remediation | Window cavity barrier around windows x 2 variations | Ben Cahill | Fire | Active | 2800 | 2800 | 0 | 0 | [6 empty] | 0
P2047 | Great Yarmouth Learning Hub -FIRE | RIBA Stage 4 - Fire Support | Ben Cahill | Fire | Active | 2500 | 2500 | 0 | 605 | [6 empty] | 0
P2047 | Great Yarmouth Learning Hub -FIRE | RIBA Stage 5 Construction - Fire Support | Ben Cahill | Fire | Active | 8900 | 6675 | 2225 | 220 | 2225 | [5 empty] | 0
P2054 | Bucklers Park - Fire | RIBA Stage 4 Technical Design Support - FIRE | Rob Holland | Fire | Active | 28900 | 14450 | 14450 | 0 | [6 empty] | 14450
P2058 | Adelaide House - Contractor Support | Additional support for stair core remedial works | Terry Marsh | Fire | Active | 2500 | 2500 | 0 | 0 | [6 empty] | 0
P2058 | Adelaide House - Contractor Support | RIBA Stage 5 ACOUSTICS - Construction (2 x site inspection) | Joe Conaghan | Acoustics | Active | 1500 | 750 | 750 | 0 |  | 750 |  |  |  |  | 0
P2058 | Adelaide House - Contractor Support | RIBA Stage 5 ACOUSTICS - Construction (RFIs) | Joe Conaghan | Acoustics | Active | 3600 | 3060 | 540 | 75 | 540 | [5 empty] | 0
P2058 | Adelaide House - Contractor Support | RIBA Stage 5 FIRE | Ben Cahill | Fire | Active | 16900 | 16900 | 0 | 1824.92 | [6 empty] | 0
P2058 | Adelaide House - Contractor Support | RIBA Stage 6 ACOUSTICS - Construction (1 x test visits) | Joe Conaghan | Acoustics | Active | 2000 | 0 | 2000 | 0 | [6 empty] | 2000
P2068 | University of Essex - Window Design Standard | Acoustics | Ben Cahill | Acoustics | Active | 3950 | 3950 | 0 | 0 | [6 empty] | 0
P2068 | University of Essex - Window Design Standard | Fire | Ben Cahill | Fire | Active | 10000 | 2000 | 8000 | 0 | [6 empty] | 8000
P2068 | University of Essex - Window Design Standard | Proposal | Ben Cahill | Acoustics | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2072 | 5 Garrett Street, London, EC1Y 0TT - Cladding alterations | Design Stage Support - Fire | Ben Cahill | Fire | Active | 7500 | 7500 | 0 | 1275 | [6 empty] | 0
P2072 | 5 Garrett Street, London, EC1Y 0TT - Cladding alterations | Facade Project Management | Ben Cahill | Fire | Active | 4500 | 1000 | 3500 | 522.5 | [6 empty] | 3500
P2072 | 5 Garrett Street, London, EC1Y 0TT - Cladding alterations | Final Completion Report | Ben Cahill | Fire | Active | 4000 | 4000 | 0 | 70 | [6 empty] | 0
P2072 | 5 Garrett Street, London, EC1Y 0TT - Cladding alterations | Implementation stage support | Ben Cahill | Fire | Active | 18000 | 0 | 18000 | 190 | [6 empty] | 18000
P2072 | 5 Garrett Street, London, EC1Y 0TT - Cladding alterations | RIBA Stage 4 | Ben Cahill | Fire | Active | 23210 | 50880 | 0 | 0 | [6 empty] | 0
P2072 | 5 Garrett Street, London, EC1Y 0TT - Cladding alterations | Survey and Investigation | Ben Cahill | Fire | Active | 3780 | 7560 | 0 | 0 | [6 empty] | 0
P2076 | LHR114 - Fire & Acoustics | LHR 114 - Cumulative Impact Report Revision | Nick Swainston | Acoustics | Active | 1450 | 1450 | 0 | 0 | [6 empty] | 0
P2076 | LHR114 - Fire & Acoustics | Master planning - Fire | Rob Holland | Fire | Active | 6720 | 6720 | 0 | 190 | [6 empty] | 0
P2101 | Capel Mottingham | Additional Fire support | Terry Marsh | Fire | Active | 2000 | 2000 | 0 | 25 | [6 empty] | 0
P2120 | Woodhouse Grade II farmhouse in Essex | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2120 | Woodhouse Grade II farmhouse in Essex | RIBA Stage 5 | Ben Cahill | Fire | Active | 3920 | 0 | 3920 | 0 | [6 empty] | 3920
P2135 | 54 Mount Ave, Hutton | Fire Strategy Report of revised layout | Ben Cahill | Fire | Active | 7800 | 0 | 7800 | 0 | 7800 | [5 empty] | 0
P2143 | Chelsea Barracks | Fee Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2143 | Chelsea Barracks | Stage 4 - Fire | Ben Cahill | Fire | Active | 3750 | 3750 | 0 | 615.29 | [6 empty] | 0
P2143 | Chelsea Barracks | Stage 5 - Fire | Ben Cahill | Fire | Active | 27100 | 27100 | 0 | 1374 | [6 empty] | 0
P2153 | Project Horizon - Fire strategy | Construction stage support (2 site visits) | Terry Marsh | Fire | Construction | 5300 | 0 | 5300 | 0 | [6 empty] | 5300
P2153 | Project Horizon - Fire strategy | Design Stage Support (including 4 meetings)) | Terry Marsh | Fire | Construction | 7600 | 7600 | 0 | 525 | [6 empty] | 0
P2153 | Project Horizon - Fire strategy | Proposal | Terry Marsh | Fire | Construction | 0 | 0 | 0 | 0 | [6 empty] | 0
P2168 | Thorpe Lee Manor, Egham - Fire | Proposal | Rob Holland | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2168 | Thorpe Lee Manor, Egham - Fire | RIBA Stage 3 - Spatial Coordination - Fire | Rob Holland | Fire | Active | 7500 | 7500 | 0 | 95 | [6 empty] | 0
P2168 | Thorpe Lee Manor, Egham - Fire | RIBA Stage 2 - Concept Design - Fire | Rob Holland | Fire | Active | 1500 | 1500 | 0 | 0 | [6 empty] | 0
P2168 | Thorpe Lee Manor, Egham - Fire | RIBA Stage 4 - Technical Design - Fire | Rob Holland | Fire | Active | 6500 | 0 | 6500 | 95 | [6 empty] | 6500
P2180 | Hull and Stevenage stations - Fire | FORM A - Hull Station | Ben Cahill | Fire | Active | 4500 | 4500 | 0 | 55 | [6 empty] | 0
P2180 | Hull and Stevenage stations - Fire | FORM A - Stevenage | Ben Cahill | Fire | Active | 5900 | 5900 | 0 | 172.5 | [6 empty] | 0
P2180 | Hull and Stevenage stations - Fire | FORM B - Stevenage | Ben Cahill | Fire | Active | 5900 | 0 | 5900 | 1640 | [6 empty] | 5900
P2180 | Hull and Stevenage stations - Fire | FORM B -Hull Station | Ben Cahill | Fire | Active | 4500 | 0 | 4500 | 55 | [6 empty] | 4500
P2186 | Hewett Academy - Norwich | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2186 | Hewett Academy - Norwich | RIBA Stage 3 - Spatial Coordination - Fire | Ben Cahill | Fire | Active | 9500 | 9500 | 0 | 280 | [6 empty] | 0
P2186 | Hewett Academy - Norwich | RIBA Stage 2 - Concept Design - Fire | Ben Cahill | Fire | Active | 5500 | 5500 | 0 | 0 | [6 empty] | 0
P2186 | Hewett Academy - Norwich | RIBA Stage 4 - Technical Design - Fire | Ben Cahill | Fire | Active | 9500 | 9500 | 0 | 1095 | [6 empty] | 0
P2186 | Hewett Academy - Norwich | RIBA Stage 5 - Manufacturing and Construction - Fire | Ben Cahill | Fire | Active | 12400 | 6195 | 6205 | 0 |  |  |  |  | 2000 |  | 4205
P2193 | Aparto Queens Court, Reading - FRAEW | Access/Contractor | Ben Cahill | Fire | Active | 14930 | 14930 | 0 | 2090 | [6 empty] | 0
P2193 | Aparto Queens Court, Reading - FRAEW | FRAEW | Ben Cahill | Fire | Active | 25000 | 25000 | 0 | 4717.5 | [6 empty] | 0
P2205 | Merton Passivhaus Schemes | RIBA Stage 4.1 | Mark Scaife | Acoustics | Active | 2175 | 2175 | 0 | 0 | [6 empty] | 0
P2205 | Merton Passivhaus Schemes | RIBA Stage 4.2 to 5 | Mark Scaife | Acoustics | Active | 7275 | 7275 | 0 | 0 | [6 empty] | 0
P2211 | Lakenheath PS - New PS & Pre-School | Proposal - Fire | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2211 | Lakenheath PS - New PS & Pre-School | RIBA Stage 3 - Fire | Ben Cahill | Fire | Active | 7800 | 7800 | 0 | 0 | [6 empty] | 0
P2211 | Lakenheath PS - New PS & Pre-School | RIBA Stage 4 - FIRE | Ben Cahill | Fire | Active | 7800 | 7800 | 0 | 720 | [6 empty] | 0
P2211 | Lakenheath PS - New PS & Pre-School | RIBA Stage 5 - FIRE | Ben Cahill | Fire | Active | 6400 | 0 | 6400 | 0 | [6 empty] | 6400
P2233 | Visitor Attraction, County Hall, London | Acoustic Stage 3 - Redesign (1302600018788) | Joe Conaghan | Acoustics | Active | 1650 | 1650 | 0 | 9440 | [6 empty] | 0
P2233 | Visitor Attraction, County Hall, London | Stage 3 - Fire (1302600018787 ) | Rob Holland | Fire | Active | 17100 | 17100 | 0 | 0 | [6 empty] | 0
P2233 | Visitor Attraction, County Hall, London | Stage 4 - Acoustics (1302600018788) | Joe Conaghan | Acoustics | Active | 2625 | 262 | 2362 | 0 |  | 1000 | 1362 |  |  |  | 0
P2233 | Visitor Attraction, County Hall, London | Stage 4 - Fire | Rob Holland | Fire | Active | 11400 | 0 | 11400 | 1742.5 |  | 3800 | 3800 | 3800 |  |  | 0
P2233 | Visitor Attraction, County Hall, London | Stage 4+ Acoustics | Joe Conaghan | Acoustics | Active | 500 | 0 | 500 | 0 | [6 empty] | 500
P2234 | All Saints Catholic School | RIBA Stage 4 - Technical Design - Fire POR002125 | Ben Cahill | Fire | Active | 7200 | 0 | 7200 | 70 | [6 empty] | 7200
P2234 | All Saints Catholic School | RIBA Stage 5 - Construction - Fire POR002125 | Ben Cahill | Fire | Active | 4800 | 0 | 4800 | 142.5 | [6 empty] | 4800
P2234 | All Saints Catholic School | Stage 4 - Acoustics | Nicolas Assiotis | Acoustics | Active | 1650 | 1650 | 0 | 0 | [6 empty] | 0
P2234 | All Saints Catholic School | Stage 5 - Acoustics | Nicolas Assiotis | Acoustics | Active | 2200 | 0 | 2200 | 0 | [6 empty] | 2200
P2234 | All Saints Catholic School | Stage 6 - Acoustics | Nicolas Assiotis | Acoustics | Active | 1150 | 0 | 1150 | 0 | [6 empty] | 1150
P2237 | Rayners Penn - Hotel and Spa | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2237 | Rayners Penn - Hotel and Spa | RIBA Stage 2 - Concept Design - Fire | Ben Cahill | Fire | Active | 8800 | 2200 | 6600 | 1892.5 | 6600 | [5 empty] | 0
P2247 | Fair Game, St Paul | Additional Slab Test | Mark Scaife | Acoustics | Active | 1250 | 1250 | 0 | 137.5 | [6 empty] | 0
P2247 | Fair Game, St Paul | Additional Slab Test 2 | Mark Scaife | Acoustics | Active | 1250 | 1250 | 0 | 293.33 | [6 empty] | 0
P2247 | Fair Game, St Paul | Design Stage Support | Mark Scaife | Acoustics | Active | 4840 | 800 | 4040 | 0 | [6 empty] | 4040
P2247 | Fair Game, St Paul | Fee Proposal | Mark Scaife | Acoustics | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2247 | Fair Game, St Paul | Pre-contract Stage Support | Mark Scaife | Acoustics | Active | 4930 | 4930 | 0 | 837.5 | [6 empty] | 0
P2262 | Travelodge, Boord Street, Greenwich | Additional work | Alison Marsh | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2277 | Carlton Lodge | Additional works | Rob Holland | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2284 | Motability Operations, London Relocation | Construction Stage- Fire | Ben Cahill | Fire | Construction | 4200 | 0 | 4200 | 0 | [6 empty] | 4200
P2284 | Motability Operations, London Relocation | Design Stage - Fire | Ben Cahill | Fire | Construction | 4900 | 4900 | 0 | 0 | [6 empty] | 0
P2284 | Motability Operations, London Relocation | Proposal | Ben Cahill | Fire | Construction | 0 | 0 | 0 | 0 | [6 empty] | 0
P2288 | Lewisham Library (LUF) | Proposal | Bethany Buck | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2288 | Lewisham Library (LUF) | RIBA Stage 3 - Spatial Coordination - Fire | Ben Cahill | Fire | Active | 7800 | 11925 | 0 | 0 | [6 empty] | 0
P2288 | Lewisham Library (LUF) | RIBA Stage 2 - Concept Design - Fire | Ben Cahill | Fire | Active | 4500 | 4500 | 0 | 0 | [6 empty] | 0
P2288 | Lewisham Library (LUF) | RIBA Stage 4 - Technical Design - Fire | Ben Cahill | Fire | Active | 8250 | 8250 | 0 | 380 | [6 empty] | 0
P2288 | Lewisham Library (LUF) | RIBA Stage 5 - Manufacturing and Construction - Fire | Ben Cahill | Fire | Active | 6600 | 0 | 6600 | 0 | [6 empty] | 6600
P2288 | Lewisham Library (LUF) | Stage 6 - Handover | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2308 | Trinity Primary school | Construction Support - Fire | Rob Holland | Fire | Active | 7400 | 0 | 7400 | 0 | [6 empty] | 7400
P2308 | Trinity Primary school | Design support - Fire | Rob Holland | Fire | Active | 7800 | 3900 | 3900 | 700 | 3900 | [5 empty] | 0
P2308 | Trinity Primary school | GLA Fire Statement | Rob Holland | Fire | Active | 3900 | 3900 | 0 | 0 | [6 empty] | 0
P2308 | Trinity Primary school | Planning Support - Fire | Rob Holland | Fire | Active | 4180 | 4180 | 0 | 2330 | [6 empty] | 0
P2308 | Trinity Primary school | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2309 | The Rectory Rd SEND, Dagenham | Construction Support - Fire | Rob Holland | Fire | Construction | 4900 | 0 | 4900 | 0 | [6 empty] | 4900
P2309 | The Rectory Rd SEND, Dagenham | Design support - Fire | Rob Holland | Fire | Construction | 4500 | 4500 | 0 | 1502.5 | [6 empty] | 0
P2309 | The Rectory Rd SEND, Dagenham | Planning Support - Fire | Rob Holland | Fire | Construction | 2500 | 2500 | 0 | 0 | [6 empty] | 0
P2309 | The Rectory Rd SEND, Dagenham | Proposal | Ben Cahill | Fire | Construction | 0 | 0 | 0 | 0 | [6 empty] | 0
P2315 | Norwich Victoria House | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2315 | Norwich Victoria House | RIBA Stage 2 - Concept Design | Ben Cahill | Fire | Active | 10900 | 5450 | 5450 | 4335 | 5450 | [5 empty] | 0
P2333 | Hassenbrook School | Proposal | Rob Holland | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2333 | Hassenbrook School | Site Inspection - Purchase Order J495/02 | Rob Holland | Fire | Active | 8500 | 2800 | 5700 | 2414.5 | [6 empty] | 5700
P2339 | Lexington Street | Due Diligence Review | Joe Conaghan | Acoustics | Active | 2775 | 2775 | 0 | 0 | [6 empty] | 0
P2339 | Lexington Street | RIBA Stage 3 + Planning Support | Joe Conaghan | Acoustics | Active | 3375 | 6750 | 0 | 700 | [6 empty] | 0
P2341 | BSC, Woodstreet | CFD Assessment for Mechanical Ventilation Approach | Rob Holland | Fire | Active | 5000 | 0 | 5000 | 2255 | [6 empty] | 5000
P2341 | BSC, Woodstreet | Computational Fluid Dynamics (CFD) | Ben Cahill | Fire | Active | 6500 | 6500 | 0 | 3862.5 | [6 empty] | 0
P2368 | ESCP Business School | Stage 2 - Acoustics | Mark Scaife | Acoustics | Active | 500 | 0 | 500 | 562.5 | 500 | [5 empty] | 0
P2368 | ESCP Business School | Stage 3 - Acoustics | Mark Scaife | Acoustics | Active | 2750 | 0 | 2750 | 0 |  | 1250 | 1500 |  |  |  | 0
P2368 | ESCP Business School | Stage 4 - Acoustics | Mark Scaife | Acoustics | Active | 1950 | 0 | 1950 | 0 |  |  |  | 1000 | 950 |  | 0
P2368 | ESCP Business School | Stage 5 - Acoustics | Mark Scaife | Acoustics | Active | 2250 | 0 | 2250 | 0 | [6 empty] | 2250
P2368 | ESCP Business School | Stage 6 - Acoustic Testing | Mark Scaife | Acoustics | Active | 2250 | 0 | 2250 | 0 | [6 empty] | 2250
P2375 | Bard & Hewett - AMZN | RIBA Stage 3 - Spatial Coordination - Fire | Ben Cahill | Fire | Active | 15600 | 15600 | 0 | 0 | [6 empty] | 0
P2375 | Bard & Hewett - AMZN | RIBA Stage 2 - Concept Design - Fire | Ben Cahill | Fire | Active | 10000 | 10000 | 0 | 0 | [6 empty] | 0
P2375 | Bard & Hewett - AMZN | RIBA Stage 4 - Technical Design - Fire | Ben Cahill | Fire | Active | 15600 | 15600 | 0 | 3210 | [6 empty] | 0
P2382 | Farnborough College of Technology Phase 1 | Design Stage - Fire | Rob Holland | Fire | Active | 10000 | 5000 | 5000 | 627.5 | [6 empty] | 5000
P2391 | Flat 6, Wedderburn Road, NW3 5QG | Plant Noise Assessment | Teli Chinelis | Acoustics | Active | 950 | 950 | 0 | 0 | [6 empty] | 0
P2391 | Flat 6, Wedderburn Road, NW3 5QG | Proposal | Teli Chinelis | Acoustics | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2394 | Theatre Building, Bow, London | Design support - Fire | Ben Cahill | Fire | Active | 6000 | 6000 | 0 | 150 | [6 empty] | 0
P2394 | Theatre Building, Bow, London | Facade Project Management | Ben Cahill | Fire | Active | 4500 | 1000 | 3500 | 0 | [6 empty] | 3500
P2394 | Theatre Building, Bow, London | Final Report | Ben Cahill | Fire | Active | 3500 | 0 | 3500 | 0 | [6 empty] | 3500
P2394 | Theatre Building, Bow, London | Implementation support - Fire | Ben Cahill | Fire | Active | 18000 | 0 | 18000 | 522.5 | [6 empty] | 18000
P2394 | Theatre Building, Bow, London | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2394 | Theatre Building, Bow, London | Riba Stage 4 - Developed Design For Tender Documentation for a traditional contract route (July & | Ben Cahill | Fire | Active | 23010 | 23010 | 0 | 0 | [6 empty] | 0
P2394 | Theatre Building, Bow, London | Survey & Investigation | Ben Cahill | Fire | Active | 3780 | 3780 | 0 | 0 | [6 empty] | 0
P2401 | Hilton Park Lane - Emergency Plant Replacement | fire safety support | Ben Cahill | Fire | Active | 8800 | 8800 | 0 | 3057.08 | [6 empty] | 0
P2401 | Hilton Park Lane - Emergency Plant Replacement | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2406 | Merchant square | Building Control Approval | Darren Watson | Building Surveying | Active | 3980 | 1990 | 1990 | 0 | [6 empty] | 1990
P2406 | Merchant square | Management of Construction Cost Control & Change Control Procedures | Darren Watson | Building Surveying | Active | 2500 | 250 | 2250 | 0 | [6 empty] | 2250
P2406 | Merchant square | Management of Project Document Creation | Darren Watson | Building Surveying | Active | 13585 | 13585 | 0 | 0 | [6 empty] | 0
P2406 | Merchant square | Pre Contract stage | Darren Watson | Building Surveying | Active | 2480 | 2480 | 0 | 380 | [6 empty] | 0
P2406 | Merchant square | Proposal | Darren Watson | Building Surveying | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2407 | Mizzen Court | Galatea - Block B Pre Contract Stage | Darren Watson | Building Surveying | Active | 1425 | 1425 | 0 | 0 | [6 empty] | 0
P2407 | Mizzen Court | Galatea B - Building Control Approval | Darren Watson | Building Surveying | Active | 1990 | 1592 | 398 | 0 | [6 empty] | 398
P2407 | Mizzen Court | Galatea B - Management Of Cost Control and Change Control Procedures | Darren Watson | Building Surveying | Active | 1250 | 125 | 1125 | 237.5 | [6 empty] | 1125
P2407 | Mizzen Court | Galatea Block A - Building Control Approval | Darren Watson | Building Surveying | Active | 1990 | 1592 | 398 | 0 | [6 empty] | 398
P2407 | Mizzen Court | Galatea Block A - Management of Construction Cost Control & Change Control Procedures | Darren Watson | Building Surveying | Active | 1250 | 125 | 1125 | 0 | [6 empty] | 1125
P2407 | Mizzen Court | Galatea Block A - Pre contract stage | Darren Watson | Building Surveying | Active | 1425 | 1425 | 0 | 380 | [6 empty] | 0
P2407 | Mizzen Court | Management of Project Document Creation | Darren Watson | Building Surveying | Active | 13585 | 13585 | 0 | 0 | [6 empty] | 0
P2407 | Mizzen Court | Proposal | Darren Watson | Building Surveying | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2435 | Aparto Queens Court - GAP Analysis | Building Safety Case Report | Darren Watson | Building Surveying | Active | 7030 | 5976 | 1054 | 5367.5 | [6 empty] | 1054
P2435 | Aparto Queens Court - GAP Analysis | Gap Analysis | Darren Watson | Building Surveying | Active | 2565 | 2565 | 0 | 1567.5 | [6 empty] | 0
P2435 | Aparto Queens Court - GAP Analysis | Proposal | Darren Watson | Building Surveying | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2436 | Aparto Caton Court - GAP Analysis | Building Safety Case Report | Darren Watson | Building Surveying | Active | 7030 | 5976 | 1054 | 2185 | [6 empty] | 1054
P2436 | Aparto Caton Court - GAP Analysis | Gap Analysis | Darren Watson | Building Surveying | Active | 2565 | 2565 | 0 | 4940 | [6 empty] | 0
P2436 | Aparto Caton Court - GAP Analysis | Proposal | Darren Watson | Building Surveying | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2443 | Kendal Court, Cambridge | Design Stage - Fire | Rob Holland | Fire | Active | 8000 | 1600 | 6400 | 260 | [6 empty] | 6400
P2443 | Kendal Court, Cambridge | Planning Support - Fire | Rob Holland | Fire | Active | 5500 | 0 | 5500 | 0 | [6 empty] | 5500
P2443 | Kendal Court, Cambridge | Proposal | Rob Holland | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2445 | Gresham's School - Morgan Sindall | Fee Proposal | Ben Cahill | Fire & Acoustics | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2445 | Gresham's School - Morgan Sindall | Stage 4 - Fire | Ben Cahill | Fire | Active | 9000 | 9000 | 0 | 7107.63 | [6 empty] | 0
P2445 | Gresham's School - Morgan Sindall | Stage 5 - Fire | Ben Cahill | Fire | Active | 13000 | 0 | 13000 | 165 | [6 empty] | 13000
P2462 | Telehouse South Day - Data Centre | Fee Proposal | Rob Holland | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2462 | Telehouse South Day - Data Centre | Stage 4 - Fire | Rob Holland | Fire | Active | 24769.5 | 24770 | 0 | 5720 | [6 empty] | 0
P2462 | Telehouse South Day - Data Centre | Stage 5 - Fire | Rob Holland | Fire | Active | 57110.48 | 10270 | 46840 | 0 | 3975 | 2850 | 2850 | 5400 | 2850 | 2850 | 26065
P2475 | St Nicholas Court, Friars Street | Construction Phase Support | Darren Watson | Fire | Active | 17000 | 0 | 17000 | 0 | [6 empty] | 17000
P2475 | St Nicholas Court, Friars Street | FRAEW Report | Darren Watson | Fire | Active | 4500 | 0 | 4500 | 0 | [6 empty] | 4500
P2475 | St Nicholas Court, Friars Street | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2475 | St Nicholas Court, Friars Street | Retrospective Fire Strategy | Darren Watson | Fire | Active | 6500 | 6500 | 0 | 0 | [6 empty] | 0
P2480 | Ricards Sixth Form | Fee Proposal | Ben Cahill | Acoustics | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2480 | Ricards Sixth Form | Stage 4 - Fire | Ben Cahill | Fire | Active | 5200 | 5200 | 0 | 560 | [6 empty] | 0
P2480 | Ricards Sixth Form | Stage 5 - Fire | Ben Cahill | Fire | Active | 9500 | 0 | 9500 | 0 | [6 empty] | 9500
P2482 | Stowmarket High School Expansion | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2482 | Stowmarket High School Expansion | RIBA Stage 3 - Spatial Coordination - Fire | Ben Cahill | Fire | Active | 4500 | 4500 | 0 | 2270 | [6 empty] | 0
P2482 | Stowmarket High School Expansion | RIBA Stage 4 - Technical Design - Fire | Ben Cahill | Fire | Active | 4500 | 4500 | 0 | 170 | [6 empty] | 0
P2482 | Stowmarket High School Expansion | RIBA Stage 5 - Construction support - Fire | Ben Cahill | Fire | Active | 7500 | 0 | 7500 | 0 | [6 empty] | 7500
P2500 | The Black Cap, Camden | Design Stage - Fire | Ben Cahill | Fire | Active | 11000 | 11000 | 0 | 905 | [6 empty] | 0
P2500 | The Black Cap, Camden | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2509 | 52 Avenue Road, St Johns Wood | Environmental Noise Survey | Nick Swainston | Acoustics | Active | 1785 | 1785 | 0 | 0 | [6 empty] | 0
P2509 | 52 Avenue Road, St Johns Wood | Site inspections | Nick Swainston | Acoustics | Active | 4250 | 0 | 4250 | 0 | [6 empty] | 4250
P2509 | 52 Avenue Road, St Johns Wood | Stage 4 - Acoustics | Nick Swainston | Acoustics | Active | 6285 | 5028 | 1257 | 2362.5 | [6 empty] | 1257
P2509 | 52 Avenue Road, St Johns Wood | Stage 4 - Fire | Ben Cahill | Fire | Active | 12000 | 9600 | 2400 | 4889.9 | [6 empty] | 2400
P2509 | 52 Avenue Road, St Johns Wood | Stage 5 - Acoustics | Nick Swainston | Acoustics | Active | 5250 | 0 | 5250 | 0 | [6 empty] | 5250
P2509 | 52 Avenue Road, St Johns Wood | Stage 5 - Fire | Ben Cahill | Fire | Active | 24000 | 0 | 24000 | 0 | [6 empty] | 24000
P2509 | 52 Avenue Road, St Johns Wood | Testing | Nick Swainston | Acoustics | Active | 1740 | 0 | 1740 | 0 | [6 empty] | 1740
P2512 | CWOA 2026 | Construction and Commissioning Stage | Mark Scaife | Acoustics | Active | 7500 | 0 | 7500 | 0 | [6 empty] | 7500
P2512 | CWOA 2026 | Design Stage Support - PO #1302600184748 | Mark Scaife | Acoustics | Active | 3750 | 3750 | 0 | 387.5 | [6 empty] | 0
P2523 | Colchester Fire Strategy Reviews | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2523 | Colchester Fire Strategy Reviews | Retrospective Fire Strategies - Appointed | Ben Cahill | Fire | Active | 30640 | 30640 | 0 | 975 | [6 empty] | 0
P2535 | Chiswick Park | Construction phase site visits * 10 | Ben Cahill | Fire | Active | 6000 | 1500 | 4500 | 0 | [6 empty] | 4500
P2535 | Chiswick Park | Construction phase support * 10 Buildings | Ben Cahill | Fire | Active | 4400 | 0 | 4400 | 352.5 | [6 empty] | 4400
P2535 | Chiswick Park | Design Stage Assessment * 10 buildings | Ben Cahill | Fire | Active | 26400 | 26400 | 0 | 1920 | [6 empty] | 0
P2535 | Chiswick Park | Fire Stair assessments - Buildings 4, 5, 7 and 12 | Ben Cahill | Fire | Active | 9800 | 9800 | 0 | 0 | [6 empty] | 0
P2535 | Chiswick Park | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2550 | Central Park, Thorpe Park | Construction and Commissioning Stage | Mark Scaife | Acoustics | Active | 7500 | 0 | 7500 | 0 | [6 empty] | 7500
P2550 | Central Park, Thorpe Park | Design Stage Support | Mark Scaife | Acoustics | Active | 3250 | 650 | 2600 | 222.5 | [6 empty] | 2600
P2550 | Central Park, Thorpe Park | Planning Stage support | Mark Scaife | Acoustics | Active | 6500 | 6500 | 0 | 0 | [6 empty] | 0
P2550 | Central Park, Thorpe Park | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2551 | Albert Mill | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2551 | Albert Mill | Third party review | Ben Cahill | Fire | Active | 5500 | 5500 | 0 | 677.5 | [6 empty] | 0
P2554 | GCB COCOA - Refurb & extension | Acoustic Planning Support | Joe Conaghan | Acoustics | Active | 7950 | 7950 | 0 | 0 | [6 empty] | 0
P2554 | GCB COCOA - Refurb & extension | RIBA Stage 4 - FIRE | Alison Marsh | Fire | Active | 7500 | 7500 | 0 | 1657.5 | [6 empty] | 0
P2554 | GCB COCOA - Refurb & extension | RIBA Stage 5 - FIRE | Alison Marsh | Fire | Active | 14480 | 0 | 14480 | 350 | [6 empty] | 14480
P2555 | Taj Hotel St James Court | Site Noise Survey & Sound Insulation Testing | Nick Swainston | Acoustics | Active | 3300 | 3300 | 0 | 0 | [6 empty] | 0
P2555 | Taj Hotel St James Court | Stage 4 - Acoustics | Nick Swainston | Acoustics | Active | 12950 | 12950 | 0 | 275 | [6 empty] | 0
P2555 | Taj Hotel St James Court | Stage 5 - Acoustics | Nick Swainston | Acoustics | Active | 4745 | 0 | 4745 | 1485 |  | 2745 | 2000 |  |  |  | 0
P2558 | East London Arts & Music (ELAM) | Environmental Noise Survey | Nick Swainston | Acoustics | Active | 1750 | 3500 | 0 | 0 | [6 empty] | 0
P2558 | East London Arts & Music (ELAM) | Section A) Architectural Acoustics | Nick Swainston | Acoustics | Active | 4225 | 2112 | 4225 | 2475 | [6 empty] | 4225
P2558 | East London Arts & Music (ELAM) | Section B) Building Services and Internal (Noise) Acoustics | Nick Swainston | Acoustics | Active | 2850 | 712 | 2850 | 287.5 | [6 empty] | 2850
P2563 | Cariba Creek, Alton Towers | Noise at work Assessment | Mark Scaife | Acoustics | Active | 3450 | 0 | 3450 | 0 |  | 3450 |  |  |  |  | 0
P2565 | GRAFTON GATE, MK | Fire Support RIBA Stage 2 | Ben Cahill | Fire | Active | 11400 | 6840 | 4560 | 585 |  | 4560 |  |  |  |  | 0
P2565 | GRAFTON GATE, MK | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2575 | Prospect House | Initial Review of Scheme | Ben Cahill | Fire | Active | 2000 | 0 | 2000 | 95 | [6 empty] | 2000
P2575 | Prospect House | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2585 | Garden House | Acoustic - Due Diligence Review and Site Visit | Joe Conaghan | Acoustics | Active | 2500 | 2500 | 0 | 2815 | [6 empty] | 0
P2585 | Garden House | Acoustic - RIBA Stage 3 Design Development | Joe Conaghan | Acoustics | Active | 2250 | 2250 | 0 | 0 | [6 empty] | 0
P2585 | Garden House | Acoustic - RIBA Stage 4 Technical Design | Joe Conaghan | Acoustics | Active | 2250 | 0 | 2250 | 0 | 2250 | [5 empty] | 0
P2585 | Garden House | Acoustic - RIBA Stage 5 Construction Stage | Joe Conaghan | Acoustics | Active | 4450 | 0 | 4450 | 0 |  |  |  | 2200 | 2250 |  | 0
P2585 | Garden House | Construction Stage - Fire (24-RF-LDN-GARDEN-01-218) | Ben Cahill | Fire | Active | 11970 | 0 | 11970 | 0 | [6 empty] | 11970
P2585 | Garden House | Design Stage - Fire (24-RF-LDN-GARDEN-01-218) | Ben Cahill | Fire | Active | 12350 | 0 | 12350 | 1872.5 | [6 empty] | 12350
P2585 | Garden House | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2588 | WCC Package B | Acoustic - Pre-Contract Testing - QPC - PO900534325 | Nick Swainston | Acoustics | Active | 2800 | 2800 | 0 | 0 | [6 empty] | 0
P2588 | WCC Package B | Acoustic - Pre-Contract Testing - Torridon - PO9005343249 | Nick Swainston | Acoustics | Active | 2800 | 2800 | 0 | 0 | [6 empty] | 0
P2588 | WCC Package B | Acoustic - Pre-Work Acoustic Progress Audit for each site - PO90053432521 | Nick Swainston | Acoustics | Active | 2800 | 2800 | 0 | 112.5 | [6 empty] | 0
P2588 | WCC Package B | Fire - Pre-Construction validation - QPC- 9005343262 | Ben Cahill | Fire | Active | 2900 | 2900 | 0 | 2063.48 | [6 empty] | 0
P2588 | WCC Package B | Fire - Pre-Construction validation - Torridon - 9005343253 | Ben Cahill | Fire | Active | 2900 | 2900 | 0 | 1822.43 | [6 empty] | 0
P2588 | WCC Package B | Fire -Pre-Construction validation - Adpar Street- 9005343261 | Ben Cahill | Fire | Active | 2900 | 2900 | 0 | 803.7 | [6 empty] | 0
P2591 | Speedwell Court, Southampton | Proposal | Rob Holland | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2591 | Speedwell Court, Southampton | Remedial works | Rob Holland | Fire | Active | 8700 | 0 | 8700 | 0 | [6 empty] | 8700
P2595 | Guildhall Yard East | Fee Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2595 | Guildhall Yard East | Stage 2 - Fire | Ben Cahill | Fire | Active | 8600 | 8600 | 0 | 150 | [6 empty] | 0
P2595 | Guildhall Yard East | Stage 3 - Fire | Ben Cahill | Fire | Active | 14350 | 14350 | 0 | 2364.97 | [6 empty] | 0
P2595 | Guildhall Yard East | Stage 4 - Fire | Ben Cahill | Fire | Active | 13500 | 0 | 13500 | 640 |  |  |  | 3375 | 3375 |  | 6750
P2595 | Guildhall Yard East | Stage 5 - Fire | Ben Cahill | Fire | Active | 23500 | 0 | 23500 | 0 | [6 empty] | 23500
P2599 | The Broadway, Landscape Tower 1 | BSR support | Rob Holland | Fire | Active | 2500 | 0 | 2500 | 0 | [6 empty] | 2500
P2599 | The Broadway, Landscape Tower 1 | Design Stage - Fire | Rob Holland | Fire | Active | 5000 | 2500 | 2500 | 375 | [6 empty] | 2500
P2599 | The Broadway, Landscape Tower 1 | Proposal | Rob Holland | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2608 | Aylesbury Britannia Walk | Fire Risk Appraisal of the external facades | Ben Cahill | Fire | Active | 5500 | 0 | 5500 | 355 | [6 empty] | 5500
P2608 | Aylesbury Britannia Walk | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2610 | 24 Stanhope Terrace | Provide Building Control Consultancy Services | Darren Watson | Building Surveying | Active | 4940 | 4940 | 0 | 142.5 | [6 empty] | 0
P2611 | Ascot High Street | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2611 | Ascot High Street | RIBA Stage 3 - Spatial Coordination - Fire | Ben Cahill | Fire | Active | 15200 | 15200 | 0 | 3545 | [6 empty] | 0
P2611 | Ascot High Street | RIBA Stage 4 - Technical Design - Fire | Ben Cahill | Fire | Active | 15200 | 0 | 15200 | 150 |  | 3800 | 3800 | 3800 | 3800 |  | 0
P2611 | Ascot High Street | RIBA Stage 5 - Manufacturing and Construction - Fire | Ben Cahill | Fire | Active | 12300 | 0 | 12300 | 0 | [6 empty] | 12300
P2612 | ADiTMC | RIBA Stage 2 + - Advanced Concept Design | Mark Scaife | Acoustics | Active | 6400 | 6400 | 0 | 0 | [6 empty] | 0
P2612 | ADiTMC | RIBA Stage 4 - Technical Design | Mark Scaife | Acoustics | Active | 8200 | 0 | 8200 | 175 |  | 3000 | 3000 | 2200 |  |  | 0
P2612 | ADiTMC | RIBA Stage 5 - Tender Review | Mark Scaife | Acoustics | Active | 4000 | 0 | 4000 | 0 |  |  |  | 2000 | 2000 |  | 0
P2638 | Flat -11 Thorourn House | Building Safety Act - Building Control Services | Darren Watson | Building Surveying | Active | 4845 | 4845 | 0 | 142.5 | [6 empty] | 0
P2638 | Flat -11 Thorourn House | Fee Proposal | Darren Watson | Building Surveying | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2650 | Solasta Riverside | Create RFI Document | Ben Cahill | Fire | Active | 2660 | 2660 | 0 | 0 | [6 empty] | 0
P2650 | Solasta Riverside | Fee Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 448.5 | [6 empty] | 0
P2650 | Solasta Riverside | Review Cause and Effect at Hines Offices | Ben Cahill | Fire | Active | 1500 | 1500 | 0 | 0 | [6 empty] | 0
P2650 | Solasta Riverside | Scrutinise Data Room Info | Ben Cahill | Fire | Active | 3040 | 3040 | 0 | 0 | [6 empty] | 0
P2650 | Solasta Riverside | Scrutinise Returned Information | Ben Cahill | Fire | Active | 3040 | 3040 | 0 | 0 | [6 empty] | 0
P2650 | Solasta Riverside | Site inspections | Ben Cahill | Fire | Active | 18240 | 18240 | 0 | 0 | [6 empty] | 0
P2668 | Creative Digital Workspace at Queen Street (Digital Forum, 43 Queen Street) | Construction stage Support - Acoustics | Nick Swainston | Acoustics | Active | 3150 | 2362 | 788 | 0 | 788 | [5 empty] | 0
P2668 | Creative Digital Workspace at Queen Street (Digital Forum, 43 Queen Street) | Construction stage Support - Fire | Ben Cahill | Fire | Active | 10640 | 3192 | 7448 | 195 | [6 empty] | 7448
P2668 | Creative Digital Workspace at Queen Street (Digital Forum, 43 Queen Street) | Fee Proposal | Nick Swainston | Acoustics | Active | 0 | 0 | 0 | 77.5 | [6 empty] | 0
P2668 | Creative Digital Workspace at Queen Street (Digital Forum, 43 Queen Street) | Fire Risk Assessment | Ben Cahill | Fire | Active | 2500 | 0 | 2500 | 0 | [6 empty] | 2500
P2671 | 125 Felixstowe Road | Fee Proposal | Darren Watson | Building Surveying | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2671 | 125 Felixstowe Road | Gateway 2 Application Coordination | Darren Watson | Building Surveying | Active | 5144.25 | 570 | 4574 | 570 | [6 empty] | 4574
P2675 | Harris Science Academy | RIBA Stage 3 - TA Review - Acoustic | Mark Scaife | Acoustics | Active | 1375 | 0 | 1375 | 612.5 | 1375 | [5 empty] | 0
P2675 | Harris Science Academy | RIBA Stage 3 - TA Review - Fire | Ben Cahill | Fire | Active | 4900 | 0 | 4900 | 0 | 2450 | 2450 |  |  |  |  | 0
P2675 | Harris Science Academy | RIBA Stage 4 - TA Review - Acoustic | Mark Scaife | Acoustics | Active | 2875 | 0 | 2875 | 0 | [6 empty] | 2875
P2675 | Harris Science Academy | RIBA Stage 4 - TA Review - Fire | Ben Cahill | Fire | Active | 6500 | 0 | 6500 | 0 | [6 empty] | 6500
P2677 | Great West Trading Estate, Brentford | Air Quality Assessment | Nicolas Assiotis | Acoustics | Active | 1950 | 0 | 1950 | 250 |  |  | 1950 |  |  |  | 0
P2677 | Great West Trading Estate, Brentford | Noise Impact Assessment | Nicolas Assiotis | Acoustics | Active | 3900 | 3900 | 0 | 740 | [6 empty] | 0
P2677 | Great West Trading Estate, Brentford | Proposal | Nicolas Assiotis | Acoustics | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2680 | Amwell View Satellite School - Buntingford | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2680 | Amwell View Satellite School - Buntingford | RIBA Stage 3 - Spatial Coordination - Fire | Ben Cahill | Fire | Active | 8900 | 0 | 8900 | 2955 | 4450 | 4450 |  |  |  |  | 0
P2680 | Amwell View Satellite School - Buntingford | RIBA Stage 3 - Spatial Coordination - Acoustic Design | Nick Swainston | Acoustics | Active | 5250 | 788 | 4462 | 1208.75 | 2212 | 2250 |  |  |  |  | 0
P2680 | Amwell View Satellite School - Buntingford | RIBA Stage 4 - Technical Design - Acoustics | Nick Swainston | Acoustics | Active | 6450 | 0 | 6450 | 570 |  |  | 2200 | 2200 | 2050 |  | 0
P2680 | Amwell View Satellite School - Buntingford | RIBA Stage 4 - Technical Design - Fire | Ben Cahill | Fire | Active | 8900 | 0 | 8900 | 0 |  |  | 4450 | 4450 |  |  | 0
P2680 | Amwell View Satellite School - Buntingford | RIBA Stage 5 - Manufacturing and Construction - Acoustics | Nick Swainston | Acoustics | Active | 3950 | 0 | 3950 | 0 | [6 empty] | 3950
P2680 | Amwell View Satellite School - Buntingford | RIBA Stage 5 - Manufacturing and Construction - Fire | Ben Cahill | Fire | Active | 13800 | 0 | 13800 | 0 | [6 empty] | 13800
P2680 | Amwell View Satellite School - Buntingford | RIBA Stage 6 - Contract Documentation & Handover - Acoustics | Nick Swainston | Acoustics | Active | 3950 | 0 | 3950 | 0 | [6 empty] | 3950
P2687 | Rochester Row - Ambit Moat | Acoustics - RIBA Stage 4 | Joe Conaghan | Acoustics | Active | 4000 | 500 | 3500 | 980 | [6 empty] | 3500
P2691 | 27-31 Charlotte Street Restaurant | Acoustic impact assessment | Nick Swainston | Acoustics | Active | 1500 | 1500 | 0 | 205 | [6 empty] | 0
P2691 | 27-31 Charlotte Street Restaurant | Fee Proposal | Nick Swainston | Acoustics | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2691 | 27-31 Charlotte Street Restaurant | Follow Up Survey | Nick Swainston | Acoustics | Active | 750 | 0 | 750 | 0 | [6 empty] | 750
P2691 | 27-31 Charlotte Street Restaurant | Internal Acoustic Assessment & Report | Nick Swainston | Acoustics | Active | 1500 | 1500 | 0 | 3055 | [6 empty] | 0
P2691 | 27-31 Charlotte Street Restaurant | Survey | Nick Swainston | Acoustics | Active | 1250 | 1250 | 0 | 0 | [6 empty] | 0
P2697 | Reach Academy, Feltham | Acoustic Review | Mark Scaife | Acoustics | Active | 1500 | 1050 | 450 | 87.5 | 450 | [5 empty] | 0
P2697 | Reach Academy, Feltham | Fire Review | Rob Holland | Fire | Active | 4800 | 1680 | 3120 | 600 |  | 3120 |  |  |  |  | 0
P2710 | Former Commercial Buildings, 240 Wherstead Road | Planning Support - Fire | Rob Holland | Fire | Active | 1200 | 0 | 1200 | 375 | [6 empty] | 1200
P2714 | Queen Marys University, Queens Building | RIBA Stage 2 | Nicolas Assiotis | Acoustics | Active | 3450 | 3450 | 0 | 0 | [6 empty] | 0
P2714 | Queen Marys University, Queens Building | RIBA Stage 3 | Mark Scaife | Acoustics | Active | 3750 | 1875 | 1875 | 2690 | 1875 | [5 empty] | 0
P2714 | Queen Marys University, Queens Building | RIBA Stage 4 | Mark Scaife | Acoustics | Active | 3950 | 0 | 3950 | 0 |  | 2000 | 1950 |  |  |  | 0
P2714 | Queen Marys University, Queens Building | RIBA Stage 5 | Mark Scaife | Acoustics | Active | 3500 | 0 | 3500 | 0 |  |  |  |  | 2000 |  | 1500
P2714 | Queen Marys University, Queens Building | Site Inspections and Testing | Mark Scaife | Acoustics | Active | 3750 | 0 | 3750 | 0 | [6 empty] | 3750
P2717 | COLP Property Store | Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2717 | COLP Property Store | RIBA Stage 3 - Spatial Coordination - Fire | Ben Cahill | Fire | Active | 7800 | 0 | 7800 | 0 |  |  | 3900 | 3900 |  |  | 0
P2717 | COLP Property Store | RIBA Stage 2 - Concept Design - Fire | Ben Cahill | Fire | Active | 5900 | 0 | 5900 | 1450 | 2950 | 2950 |  |  |  |  | 0
P2717 | COLP Property Store | RIBA Stage 4 - Technical Design - Fire | Ben Cahill | Fire | Active | 7800 | 0 | 7800 | 0 | [6 empty] | 7800
P2717 | COLP Property Store | RIBA Stage 5 - Manufacturing and Construction - Fire | Ben Cahill | Fire | Active | 14500 | 0 | 14500 | 0 | [6 empty] | 14500
P2722 | Sutton Life Centre | Acoustic - Site Inspections and Testing | Mark Scaife | Acoustics | Active | 3350 | 0 | 3350 | 0 | [6 empty] | 3350
P2722 | Sutton Life Centre | Contract Documentation - Acoustics | Mark Scaife | Acoustics | Active | 3200 | 0 | 3200 | 0 |  | 1200 | 1000 | 1000 |  |  | 0
P2722 | Sutton Life Centre | Detailed Design - Acoustics | Mark Scaife | Acoustics | Active | 3195 | 1598 | 1598 | 1140 | 1598 | [5 empty] | 0
P2723 | Melrose Education | Stage 4 - Fire | Ben Cahill | Fire | Active | 7200 | 7200 | 0 | 290 | [6 empty] | 0
P2731 | The Sixth Form College - Colchester | Compartmentation Survey + Report | Darren Watson | Building Surveying | Active | 9500 | 15675 | 0 | 4002.5 | [6 empty] | 0
P2731 | The Sixth Form College - Colchester | Fee Proposal | Darren Watson | Building Surveying | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2732 | IICEC - UOW | Acoustic Proposal | Nick Swainston | Acoustics | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2732 | IICEC - UOW | Planning Application Support PO : UOW100027257 | Nick Swainston | Acoustics | Active | 1485 | 520 | 965 | 1698.5 | 965 | [5 empty] | 0
P2732 | IICEC - UOW | RIBA Stage 2 - Fire - PO: UOW100027421 | Ben Cahill | Fire | Active | 4500 | 0 | 4500 | 3935 | 2250 | 2250 |  |  |  |  | 0
P2732 | IICEC - UOW | RIBA Stage 3 - Acoustics PO: UOW100027257 | Nick Swainston | Acoustics | Active | 2795 | 699 | 2096 | 224.19 | 1096 | 1000 |  |  |  |  | 0
P2732 | IICEC - UOW | RIBA Stage 3 - Fire- PO: UOW100027421 | Ben Cahill | Fire | Active | 7200 | 0 | 7200 | 0 |  |  | 3600 | 3600 |  |  | 0
P2732 | IICEC - UOW | RIBA Stage 4 - Acoustics PO:UOW100027257 | Nick Swainston | Acoustics | Active | 4275 | 0 | 4275 | 0 |  |  | 2275 | 2000 |  |  | 0
P2734 | Former Revolution Bar | Planning Stage - Fire statement | Ben Cahill | Fire | Active | 3750 | 0 | 3750 | 1395 | 3750 | [5 empty] | 0
P2738 | Sandy School - Phase 8 | Design & Construction support | Ben Cahill | Fire | Active | 3900 | 0 | 3900 | 140 | 3900 | [5 empty] | 0
P2738 | Sandy School - Phase 8 | Fee Proposal | Ben Cahill | Fire | Active | 0 | 0 | 0 | 0 | [6 empty] | 0
P2738 | Sandy School - Phase 8 | Site Visit | Ben Cahill | Fire | Active | 1200 | 0 | 1200 | 682.36 | 1200 | [5 empty] | 0
P2740 | Marlborough Sports Garden | Acoustic Testing | Nicolas Assiotis | Acoustics | Active | 1950 | 0 | 1950 | 0 | [6 empty] | 1950
P2740 | Marlborough Sports Garden | Site Inspection - Acoustics | Nicolas Assiotis | Acoustics | Active | 1200 | 0 | 1200 | 0 | [6 empty] | 1200
P2740 | Marlborough Sports Garden | Stage 4 - Acoustics | Nicolas Assiotis | Acoustics | Active | 2750 | 0 | 2750 | 295 | 2750 | [5 empty] | 0
P2740 | Marlborough Sports Garden | Stage 4 - Fire | Ben Cahill | Fire | Active | 6500 | 0 | 6500 | 660 | 3250 | 3250 |  |  |  |  | 0
P2740 | Marlborough Sports Garden | Stage 5 - Acoustics | Nicolas Assiotis | Acoustics | Active | 2500 | 0 | 2500 | 0 |  | 1250 | 1250 |  |  |  | 0
P2740 | Marlborough Sports Garden | Stage 5 - Fire | Ben Cahill | Fire | Active | 6200 | 0 | 6200 | 0 | [6 empty] | 6200
P2746 | Northgate HS, Ipswich | RIBA Stage 3 - Spatial Coordination - Fire | Ben Cahill | Fire | Active | 7600 | 0 | 7600 | 120 | 3800 | 3800 |  |  |  |  | 0
P2746 | Northgate HS, Ipswich | RIBA Stage 4 - Technical Design - Fire | Ben Cahill | Fire | Active | 6500 | 0 | 6500 | 0 |  |  |  | 3250 | 3250 |  | 0
P2750 | 100 Queens Gate Curio by Hilton | Acoustic Testing | Nicolas Assiotis | Acoustics | Active | 1600 | 1600 | 0 | 2049.68 | [6 empty] | 0
P2757 | Portakabin Acoustic Testing | PCT | Mark Scaife | Acoustics | Active | 1220 | 0 | 1220 | 0 | 1220 | [5 empty] | 0
P2763 | Flat C 25 Fitzroy Square | Post-Construction Testing | Nicolas Assiotis | Acoustics | Active | 1600 | 0 | 1600 | 0 | [6 empty] | 1600
P2763 | Flat C 25 Fitzroy Square | Pre-Construction Testing | Nicolas Assiotis | Acoustics | Active | 1855 | 0 | 1855 | 0 | 1855 | [5 empty] | 0
P2772 | Bear Grylls - Strip out | Noise Assessment | Mark Scaife | Acoustics | Active | 3900 | 0 | 3900 | 0 | 3900 | [5 empty] | 0
P2772 | Bear Grylls - Strip out | Strip out Support | Ben Cahill | Fire | Active | 4500 | 0 | 4500 | 0 | [6 empty] | 4500
P2775 | CWoAR Fuel Lines - Vibration | Construction Impact Assessment | Nicolas Assiotis | Acoustics | Active | 1600 | 0 | 1600 | 0 | 800 | 800 |  |  |  |  | 0
P2775 | CWoAR Fuel Lines - Vibration | Operational Vibration Assessment | Nicolas Assiotis | Acoustics | Active | 2000 | 0 | 2000 | 0 | 1000 | 1000 |  |  |  |  | 0
P2775 | CWoAR Fuel Lines - Vibration | Vibration Assessment | Nicolas Assiotis | Acoustics | Active | 3300 | 0 | 3300 | 200 | 1750 | 1550 |  |  |  |  | 0

## Forecast
Row Labels | Sum of [Agreed_Fee_and_Cap] | Sum of [Invoiced_Ex_Tax] | Sum of [WIP] | Sum of Forecast This Month | Sum of Forecast Next Month | Sum of Forecast Month +2 | Sum of Forecast Month +3 | Sum of Forecast Month +4 | Sum of Forecast Month +5 | Sum of Forecast Beyond
Acoustics | 415554.5 | 201819 | 44624.01 | 34630 | 29025 | 21787 | 15850 | 12380 | 3670 | 105492
Building Surveying | 89079.25 | 81286 | 19915 | [6 empty] | 13968
Fire | 1794534.98 | 1070888 | 119411.03 | 65270 | 40405 | 33025 | 34700 | 15275 | 10200 | 561682
Fire & Acoustics | 0 | 0 | 0 | [6 empty] | 0
Grand Total | 2299168.73 | 1353993 | 183950.04 | 99900 | 69430 | 54812 | 50550 | 27655 | 13870 | 681142
Screen Grab